## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Vinod | 2026-08-27 | Import error: NegotiationArena referenced a missing negotiationState utility/module. | Sprint 2 | Vinod | Logical | Corrected import path and aligned module exports. | 2026-08-27 | Closed | Verified after application restart.
2 | Yashwanth | 2026-08-29 | NegotiationArena had JSX parse errors caused by unmatched or extra closing braces. | Sprint 2 | Yashwanth | Logical | Replaced inconsistent JSX structure with a balanced component structure. | 2026-08-29 | Closed | Vite build completed successfully.
3 | Vinod | 2026-08-30 | createOffer was imported from negotiationState although it was defined in offer.js. | Sprint 2 | Vinod | Logical | Imported createOffer from the correct offer model file. | 2026-08-30 | Closed | Offer creation tested successfully.
4 | Yashwanth | 2026-09-01 | handleMakeOffer was referenced in the UI but was not defined in NegotiationArena. | Sprint 3 | Yashwanth | Logical | Added the missing handler and connected it to offer creation and state updates. | 2026-09-01 | Closed | Make Offer works correctly.
5 | Sinchana | 2026-08-24 | Scenario/configuration navigation did not match the required flow for predefined and customizable setup. | Sprint 1 | Sinchana | User Interface | Updated flow to Scenario Selection → Configuration Choice → Agent Configuration. | 2026-08-25 | Closed | Both flows were reviewed by the team.
6 | Vinod | 2026-09-01 | Negotiation dashboard temporarily rendered blank after component integration. | Sprint 3 | Vinod | Logical | Fixed component imports and runtime errors. | 2026-09-01 | Closed | Dashboard loads correctly.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others